## Roadmap
Sprint | Task | Status | Updated | Notes
BillGo | Tách BillGo khỏi quản lý khách hàng và danh sách việc | Hoàn thành | 2026-07-09
Location | Tự động lưu GPS sau đăng nhập | Hoàn thành | 2026-07-09 | Khách và thợ; từ chối quyền không chặn đăng nhập
Multi-service | Bộ chọn dịch vụ phân cấp cho khách, thợ và admin | Hoàn thành | 2026-07-09 | Tái sử dụng job_services và fallback service_id
Sprint nen tang mo rong | Feature Registry va Dynamic Menu cho trang Tho | Hoan thanh | 2026-07-09 | Menu tho sinh tu registry; BillGo chi hien khi tai khoan co du lieu BillGo.
BillGo | Chuan hoa dung truoc - thu sau va han thanh toan ngay 20 | Hoan thanh | 2026-07-09 | Moi ky co period_start, period_end, due_date va status tinh theo han.
Worker access control | Loc module va dich vu theo nganh nghe tho da duyet | Hoan thanh | 2026-07-10 | Fallback an toan chi hien Cong viec, Khach hang, Ho so khi chua co nganh.
Worker sales inventory | Remove BillGo from worker inventory product setup and sales order creation | Hoan thanh | 2026-07-12 | Kho hang/ban hang cua tho chi phuc vu ban hang; BillGo giu o module rieng.
Worker sales inventory | Remove BillGo from worker inventory product setup and sales order creation | Hoan thanh | 2026-07-12 | Kho hang/ban hang cua tho chi phuc vu ban hang; BillGo giu o module rieng.
2026-07-12 | Worker Sales/Inventory | Done | Tự động tạo mã sản phẩm theo danh mục khi thợ thêm sản phẩm; giữ mã khi sửa sản phẩm. | feat: tự động tạo mã sản phẩm theo danh mục | pending
2026-07-12 | Worker Dashboard | Done | Thêm thống kê hôm nay cho bảng điều khiển thợ: khách hàng, đánh giá, tổng tiền. | feat(worker-dashboard): add today stats | pending
2026-07-12 | Worker Dashboard | Done | Gộp thống kê hôm nay vào card tổng quan, hiển thị Tháng 7/Hôm nay 12/07 và thêm nút nổi Tạo việc trên mobile. | feat(worker-dashboard): optimize mobile stats layout | pending
2026-07-13 | Worker backlog jobs | Done | ??i n?t mobile C?ng vi?c th?nh T?n vi?c, li?n k?t t?i danh s?ch vi?c c? ch?a l?m v? gi? n?t + m? t?o vi?c nhanh. | feat(worker): show old backlog jobs | pending

## Commit Tracker
STT | Sprint | Commit | Status | Date | Git Hash | Notes
1 | BillGo | Separate BillGo module from customer management | Sẵn sàng commit | 2026-07-09 |  | Tách trang, dữ liệu và luồng tạo khách thu cước
2 | Location | feat(location): auto save user location on login | Sẵn sàng commit | 2026-07-09 |  | GPS login 100m hoặc 5 phút
3 | Multi-service | feat: support multi-service job with hierarchical service selector | Sẵn sàng commit | 2026-07-09 |  | Một commit; tree checkbox dùng chung
4 | Sprint nen tang mo rong | feat(worker): add feature registry and dynamic module menu system | San sang commit | 2026-07-09 | pending | Cap nhat hash sau khi tao commit.
5 | BillGo | feat(billgo): implement postpaid billing cycle with due date management | San sang commit | 2026-07-09 | pending | Cap nhat hash sau khi tao commit.
6 | Worker access control | fix(worker): filter worker modules and services by approved categories | San sang commit | 2026-07-10 | pending | Cap nhat hash sau khi tao commit.
8 | Worker specialization filter | fix(worker): prevent cross-category service matches | Committed | 2026-07-10 | current commit | Fix PC worker page showing unrelated service categories caused by generic child-service name matching.
8 | Worker specialization filter | fix(worker): prevent cross-category service matches | Committed | 2026-07-10 | current commit | Fix PC worker page showing unrelated service categories caused by generic child-service name matching.
9 | Worker sales inventory | fix(worker-sales): keep BillGo out of inventory sales | Ready to commit | 2026-07-12 | pending | Removed BillGo controls from worker inventory/sales; sales RPC always disables BillGo creation.
10 | Worker sales inventory | fix(worker-sales): keep BillGo out of inventory sales | Ready to commit | 2026-07-12 | pending | Removed BillGo controls from worker inventory/sales; sales RPC always disables BillGo creation.
2026-07-12 | feat: tự động tạo mã sản phẩm theo danh mục | pending | Worker inventory product code auto-generation by category prefix, per worker scope, duplicate handling, migration for missing codes.
2026-07-12 | feat(worker-dashboard): add today stats | pending | Add compact today customer, rating, and collected amount stats below worker dashboard summary.
2026-07-12 | feat(worker-dashboard): optimize mobile stats layout | pending | Optimize worker dashboard stats layout for mobile and add floating quick job action.
2026-07-13 | feat(worker): show old backlog jobs | pending | Mobile worker nav uses T?n vi?c for unfinished jobs from previous months and + opens quick job form.

## Bug Tracker
STT | Bug | Status | Date | Fix Commit | Notes
1 | Trang tho hien tat ca nganh nghe/dich vu khong dung specialties | Da sua | 46213 | fix(worker): filter worker modules and services by approved categories | Doi sang strict specialty filtering cho menu va quick job services.
1 | Worker page shows unrelated services for workers registered to limited categories | Fixed in pending commit | High | 2026-07-10 | fix(worker): prevent cross-category service matches | Service matching no longer allows broad child labels such as Lap dat/Sua chua to match across industries.
1 | Worker page shows unrelated services for workers registered to limited categories | Fixed in pending commit | High | 2026-07-10 | fix(worker): prevent cross-category service matches | Service matching no longer allows broad child labels such as Lap dat/Sua chua to match across industries.
2 | Worker inventory/sales exposes BillGo flow for normal worker product sales | Fixed in pending commit | 2026-07-12 | fix(worker-sales): keep BillGo out of inventory sales | Removed recurring BillGo product flag UI and disabled BillGo creation from sales orders.
3 | Worker inventory/sales exposes BillGo flow for normal worker product sales | Fixed in pending commit | 2026-07-12 | fix(worker-sales): keep BillGo out of inventory sales | Removed recurring BillGo product flag UI and disabled BillGo creation from sales orders.
2026-07-12 | Worker inventory product code collision | Fixed | Không lấy tổng số sản phẩm + 1; lấy số lớn nhất theo tiền tố trong từng worker rồi cộng 1, retry khi insert trùng. | feat: tự động tạo mã sản phẩm theo danh mục
2026-07-12 | Worker dashboard lacks daily operational stats | Fixed | Bổ sung hàng thống kê hôm nay và format tiền gọn. | feat(worker-dashboard): add today stats
2026-07-12 | Quick job action pushed too low on mobile | Fixed | Gộp hàng Hôm nay vào cùng card thống kê, thêm nút nổi Tạo việc. | feat(worker-dashboard): optimize mobile stats layout
2026-07-13 | Mobile C?ng vi?c label and link did not match old unfinished job workflow | Fixed | ??i nh?n th?nh T?n vi?c, l?c b? vi?c th?ng hi?n t?i v? s?a n?t + v? t?o vi?c nhanh. | feat(worker): show old backlog jobs

## Feature Backlog
STT | Feature | Sprint | Status | Commit | Notes
1 | Trang BillGo riêng cho khách thu cước định kỳ | BillGo | Hoàn thành | Separate BillGo module from customer management
2 | Tự động cập nhật vị trí khi đăng nhập | Location | Hoàn thành | feat(location): auto save user location on login | Thông báo GPS nhỏ khi cập nhật thành công
3 | Multi-service job với hierarchical selector | Multi-service | Hoàn thành | feat: support multi-service job with hierarchical service selector | Khách, thợ tạo nhanh, admin tạo job
4 | Feature Registry va Dynamic Menu trang Tho | Sprint nen tang mo rong | Hoan thanh | feat(worker): add feature registry and dynamic module menu system | Nen tang module theo quyen/nganh nghe/du lieu thuc te.
5 | BillGo postpaid billing cycle | BillGo | Hoan thanh | feat(billgo): implement postpaid billing cycle with due date management | Ho tro chu ky 1/3/6/12 thang va due date ngay 20 thang sau.
6 | Filter worker modules/services by approved categories | Worker access control | Hoan thanh | fix(worker): filter worker modules and services by approved categories | Ap dung cho menu worker va tao viec nhanh.
8 | Worker category-scoped service display | Worker specialization filter | Done | 2026-07-10 | fix(worker): prevent cross-category service matches | Quick job/service lists now respect approved worker categories more strictly.
8 | Worker category-scoped service display | Worker specialization filter | Done | 2026-07-10 | fix(worker): prevent cross-category service matches | Quick job/service lists now respect approved worker categories more strictly.
9 | Keep BillGo out of worker inventory sales flow | Worker sales inventory | Done | fix(worker-sales): keep BillGo out of inventory sales | Inventory products and sales orders are worker-only sales data; BillGo remains a separate module.
10 | Keep BillGo out of worker inventory sales flow | Worker sales inventory | Done | fix(worker-sales): keep BillGo out of inventory sales | Inventory products and sales orders are worker-only sales data; BillGo remains a separate module.
2026-07-12 | Auto product code by category | Done | NET/CAM/PC/PRI/SP prefix, readonly auto field, custom code override, search by SKU already supported. | feat: tự động tạo mã sản phẩm theo danh mục
2026-07-12 | Worker dashboard today stats | Done | Hiển thị khách hôm nay, đánh giá hôm nay, tổng tiền hôm nay. | feat(worker-dashboard): add today stats
2026-07-12 | Worker dashboard mobile quick action | Done | Nút nổi Tạo việc mở form tạo việc nhanh và cuộn tới đúng khu vực. | feat(worker-dashboard): optimize mobile stats layout
2026-07-13 | Worker old backlog jobs list | Worker mobile | Done | feat(worker): show old backlog jobs | Hi?n th? vi?c ch?a ho?n th?nh t? c?c th?ng tr??c; kh?ng hi?n th? vi?c trong th?ng hi?n t?i.

## Data Rules
STT | Date | Table / Area | Rule / Change | Migration | Commit
1 | 2026-07-09 | billgo_subscriptions, billgo_receivables | Khách BillGo được xác định bằng subscription; cho phép hồ sơ độc lập, không thay đổi khách cũ | migration_separate_billgo_customers.sql
2 | 2026-07-09 | profiles | Thêm latitude, longitude, last_location_at, location_updated_by | migration_login_location.sql | feat(location): auto save user location on login
3 | 2026-07-09 | jobs / job_services | Job mới lưu quan hệ nhiều-nhiều; jobs.service_id giữ làm primary và fallback legacy | migration_smart_service_workflow.sql | feat: support multi-service job with hierarchical service selector
4 | 2026-07-09 | Worker Feature Registry | Khong doi schema; dieu kien BillGo doc tu billgo_subscriptions/billgo_receivables. | Khong co | feat(worker): add feature registry and dynamic module menu system
5 | 2026-07-09 | billgo_receivables | Them status not_due/due; backfill period_start, period_end, due_date theo postpaid. | migration_billgo_postpaid_cycles.sql | feat(billgo): implement postpaid billing cycle with due date management

## Service Category
STT | Service | Status | Mapping | Notes

## Notes
STT | Date | Decision | Reason | Commit
1 | 2026-07-09 | BillGo là module riêng, không tự động đưa mọi khách Internet vào danh sách thu cước | Tránh trộn khách thường với khách thu cước định kỳ
2 | 2026-07-09 | GPS đăng nhập là best-effort | Từ chối hoặc lỗi GPS không được chặn đăng nhập | feat(location): auto save user location on login
3 | 2026-07-09 | Không tạo migration trùng job_services | Migration workflow hiện có đã tạo bảng, index và backfill; chỉ tái sử dụng | feat: support multi-service job with hierarchical service selector
4 | 2026-07-09 | Menu tho chuyen sang Feature Registry | Chuan bi mo rong module theo nganh nghe, quyen han va du lieu su dung. | feat(worker): add feature registry and dynamic module menu system
5 | 2026-07-09 | BillGo dung truoc - thu sau | Han thanh toan la ngay 20 cua thang ke tiep sau ky su dung. | feat(billgo): implement postpaid billing cycle with due date management
6 | 2026-07-10 | Worker specialties la dieu kien hien thi module/dich vu | Tho khong co nganh ro rang khong thay module nganh chuyen biet. | fix(worker): filter worker modules and services by approved categories
8 | 2026-07-10 | Worker service filtering must be category-aware; generic child service labels cannot be used as cross-industry matches. | fix(worker): prevent cross-category service matches
8 | 2026-07-10 | Worker service filtering must be category-aware; generic child service labels cannot be used as cross-industry matches. | fix(worker): prevent cross-category service matches